## Sheet1
ID | Date raised | Risk description | Likelihood | Impact | Owner | Mitigating action | Contingent action | Progress on actions | Status
1 | 2019-08-11 | Project being incomplete | Medium | High | Everyone | - Consistent planning - Agile plan - Constant communication - Epic creation | - Communication with client about what can be missed, what their priorities are, and how we will accommodate them | - Constant planning, meetings and current planning of database (and Epic) | Open | https://management.simplicable.com/management/new/130-project-risks
2 | 2019-08-11 | Story takes longer to implement than first thought | Medium | High | Everyone | - Track schedules - Assist when someone seems to be struggling - Talk to client about priority of story - Reasses amongst Epic | - Communication with client about what can be missed, what their priorities are, and how we will accommodate them | - Constant planning, meetings and current planning of database (and Epic) | Open
3 | 2019-08-11 | Group conflict | Low | Medium | Everyone | - Keep communication happening - Try not to leave issues last minute to reduce stress of the group - Be nice! | - Address the issue straight away - Get the whole story so there's no miscommunication - Let the members meet separately to discuss | - Currently not at a stressful pace | Open
4 | 2019-08-11 | Last minute happenings | Low | Medium | Everyone | - If it happens, it happens | - Refer back to Epic, see if anyone else can tackle the task if high priority | - Knowledge of all timetables, who's free when and meet when we are all free | Open
5 | 2019-08-11 | Client stops responding | Low | High | Everyone | - Keep up meetings with client to continue the creation of a more comprehensive plan | - Continue project with everything you're certain of - Start creation of decision record when there are larger decisions. If there are issues, helps to explain to client why chose a specific path | - Clients have noted they are free at the club room if they were to stop responding | Open
6 | 2019-08-11 | Client has unattainable expectation (given current level of knowledge) | Low | Medium | Everyone | - Communicate current abilities with client - Creation of backlog that will be checked with client | - Attempt to research new idea - Construct plan of way you may be able to do it, show client - If unhappy, ask again about priorities | - Current planning of project, seems doable so far | Open
7 | 2019-08-11 | Team adds own features not within the scope | Low | Medium | Everyone | - Constant reassesment of what the project requires - Keep communication with the client on what they require | - Asking client whether this was something they wanted will put things into perspective for the team - Focus on time management | - Current planning of project execution | Open
8 | 2019-08-11 | Dependencies inaccurate | Low | Medium | Everyone | - Constant reassesment of what the project requires - Communicate with client on taking longer on a specific item - Review backlog, change stories | - Need a formalised understanding of project before starting and being confident in its requirements | - Current planning of project execution | Open
9 | 2019-08-11 | Activities missing from scope (hence making time taken a lot longer) | Low | Medium | Everyone | - Constant reassesment of what the project requires - Communicate with client on taking longer on a specific item - Review backlog, change stories | - Need a formalised understanding of project before starting and being confident in its requirements | - Current planning of project execution | Open
10 | 2019-08-11 | Confusion on requirements | Low | Medium | Everyone | - Communicate with team! - Group coding sessions so we all learn | - Need a formalised understanding of project before starting and being confident in its requirements | - Current planning of project execution | Open
11 | 2019-08-11 | Lack of communication from team member | Medium | Medium | Everyone | - Keep everyone unstressed by planning and using empathy - Don't hassle in meetings - Treat them as a partner, not just a colleague | - Talk to unit coordinator | - Meetings are at the same time every week so there is less reason for someone to be 'not free' | Open
12 | 2019-08-11 | Misperception of how long it will take to learn parts of the project | Low | Medium | Everyone | - Communicate with team! - Group coding sessions so we all learn | - Need a formalised understanding of project before starting and being confident in its requirements | - Current planning of project execution | Open
13 | 2019-08-11 | Low motivation towards the end | High | High | Everyone | - Keep everyone unstressed by planning and using empathy - Don't hassle in meetings - Treat them as a partner, not just a colleague | - Communicate with unit coordinator | - N/A | Open
14 | 2019-08-11 | Database doesn't work | Medium | High | Everyone | - Constant checking - Constant testing | - Backtrack - Remove unnecessary features | - N/A | Open
15 | 2019-08-13 | Database Deployment Failures | Low | Medium | Everyone | - Constant checking - Constant testing | - Backtrack - Remove unnecessary features | - N/A | Open
16 | 2019-08-14 | Database inconsistencies | Medium | Medium | Everyone | - Constant checking - Record everything you have changed | - Due to records, easier to backtrack and see what needs to be changed - Let team leader know that a task will take longer than expected so that more focus can be put on it | - N/A | Open
17 | 2019-08-14 | Project isn't secure | Medium | Medium | Everyone | - Constant checking - Constant testing | - Communicate with client that it's out of our domain of knowledge - Focus on other areas | - N/A | Open